## Sheet1
Task | Start Date | End Date | Status | Parent Slide Deck | Task Order | Sort Key | Is Parent | DisplayLabel
Phase 0: Planning | 2030-01-07 | 2030-01-11 | Complete | Planning | -1 | 0 | TRUE | 0000 - Phase 0: Planning
Kickoff + scope alignment | 2030-01-07 | 2030-01-08 | Complete | Planning | 1 | 1 | FALSE | 0001 - Kickoff + scope alignment
Tracker setup + reporting cadence | 2030-01-08 | 2030-01-11 | Complete | Planning | 2 | 2 | FALSE | 0002 - Tracker setup + reporting cadence
Phase 1: Build | 2030-01-14 | 2030-02-15 | In Progress | Build | -1 | 10 | TRUE | 0010 - Phase 1: Build
Draft Week 1 content package | 2030-01-14 | 2030-01-25 | Complete | Build | 1 | 11 | FALSE | 0011 - Draft Week 1 content package
Draft Week 2 content package | 2030-01-21 | 2030-02-01 | In Progress | Build | 2 | 12 | FALSE | 0012 - Draft Week 2 content package
Draft Week 3 content package | 2030-01-28 | 2030-02-08 | Pending | Build | 3 | 13 | FALSE | 0013 - Draft Week 3 content package
Phase 2: Review | 2030-02-18 | 2030-03-15 | Upcoming | Review | -1 | 20 | TRUE | 0020 - Phase 2: Review
Stakeholder review pass | 2030-02-18 | 2030-03-01 | Upcoming | Review | 1 | 21 | FALSE | 0021 - Stakeholder review pass
Incorporate edits + finalize | 2030-03-04 | 2030-03-15 | Upcoming | Review | 2 | 22 | FALSE | 0022 - Incorporate edits + finalize
Phase 3: Launch | 2030-03-18 | 2030-03-22 | Upcoming | Launch | -1 | 30 | TRUE | 0030 - Phase 3: Launch
Publish materials + handoff | 2030-03-18 | 2030-03-22 | Upcoming | Launch | 1 | 31 | FALSE | 0031 - Publish materials + handoff